## Gantt
Quran Memorization App: Project-1 Timeline
23 Aug 2026 to 16 Dec 2026 ¦ Weeks start on Sunday ¦ ◆ = deadline
Phase / Task | Start | End | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17
|  |  | 2026-08-23 | 2026-08-30 | 2026-09-06 | 2026-09-13 | 2026-09-20 | 2026-09-27 | 2026-10-04 | 2026-10-11 | 2026-10-18 | 2026-10-25 | 2026-11-01 | 2026-11-08 | 2026-11-15 | 2026-11-22 | 2026-11-29 | 2026-12-06 | 2026-12-13
Phase 1: Project Initiation & Introduction (Chapter 1) | 2026-08-23 | 2026-10-08
Conduct team meetings to establish background | 2026-08-23 | 2026-08-28 | bar: 2026-08-23
Formulate precise problem statement | 2026-08-29 | 2026-09-03 | bar: 2026-08-30
Define main project aim and measurable objectives | 2026-09-04 | 2026-09-08 | bar: 2026-08-30 to 2026-09-06
Research and review related existing systems | 2026-09-09 | 2026-09-15 | bar: 2026-09-06 to 2026-09-13
Summarize findings into Project Idea and Abstract ◆ | 2026-09-16 | 2026-10-01 | bar: 2026-09-13 to 2026-09-27
Draft Chapter 1 for Final Report ◆ | 2026-09-20 | 2026-10-05 | bar: 2026-09-20 to 2026-10-04
Complete Project Proposal submission ◆ | 2026-10-06 | 2026-10-08 | bar: 2026-10-04
Phase 2: Project Planning Phase (Chapter 2) | 2026-09-01 | 2026-10-15
Define project scope and context boundaries | 2026-09-01 | 2026-09-10 | bar: 2026-08-30 to 2026-09-06
Identify and document project and product risks | 2026-09-11 | 2026-09-20 | bar: 2026-09-06 to 2026-09-20
Outline software and hardware requirements | 2026-09-21 | 2026-09-30 | bar: 2026-09-20 to 2026-09-27
Create detailed project schedule and Gantt chart | 2026-10-01 | 2026-10-10 | bar: 2026-09-27 to 2026-10-04
Review and compile Chapter 2 sections ◆ | 2026-10-11 | 2026-10-15 | bar: 2026-10-11
Phase 3: Technical Feasibility & Model Validation | 2026-09-09 | 2026-10-22
Research speech recognition models & compare licenses | 2026-09-09 | 2026-09-17 | bar: 2026-09-06 to 2026-09-13
Set up development environment and test models | 2026-09-18 | 2026-09-30 | bar: 2026-09-13 to 2026-09-27
Develop basic word-level comparison prototype | 2026-10-01 | 2026-10-15 | bar: 2026-09-27 to 2026-10-11
Evaluate prototype and validate model choice ◆ | 2026-10-16 | 2026-10-22 | bar: 2026-10-11 to 2026-10-18
Phase 4: Requirements Engineering & Analysis (Chapter 3) | 2026-09-20 | 2026-10-25
Execute requirements collection techniques | 2026-09-20 | 2026-09-30 | bar: 2026-09-20 to 2026-09-27
Define Functional Requirements and list system features | 2026-10-01 | 2026-10-08 | bar: 2026-09-27 to 2026-10-04
Identify Nonfunctional Requirements (quality & constraints) | 2026-10-09 | 2026-10-12 | bar: 2026-10-04 to 2026-10-11
Draw UML Use Case Diagrams for system interactions | 2026-10-13 | 2026-10-18 | bar: 2026-10-11 to 2026-10-18
Document detailed Use Case main flows and alternatives | 2026-10-19 | 2026-10-23 | bar: 2026-10-18
Finalize Chapter 3 compilation ◆ | 2026-10-24 | 2026-10-25 | bar: 2026-10-18 to 2026-10-25
Phase 5: System Architecture & Design (Chapter 4 - Part 1) | 2026-10-15 | 2026-11-05
Draft overall software architecture models | 2026-10-15 | 2026-10-22 | bar: 2026-10-11 to 2026-10-18
Map Use Cases to internal interactions via Sequence Diagrams | 2026-10-23 | 2026-10-28 | bar: 2026-10-18 to 2026-10-25
Design Class Diagrams including attributes and methods | 2026-10-25 | 2026-10-31 | bar: 2026-10-25
Structure Data Storage Organization and DB schema | 2026-11-01 | 2026-11-04 | bar: 2026-11-01
Finalize System Design documentation ◆ | 2026-11-04 | 2026-11-05 | bar: 2026-11-01
Phase 6: UI/UX Prototyping & Design Validation (Chapter 4 - Part 2) | 2026-10-18 | 2026-12-03
Sketch user flows and low-fidelity wireframes | 2026-10-18 | 2026-10-26 | bar: 2026-10-18 to 2026-10-25
Design high-fidelity UI screens (Roadmap, Lesson, Stats) | 2026-10-27 | 2026-11-10 | bar: 2026-10-25 to 2026-11-08
Link screens into a clickable interactive prototype ◆ | 2026-11-11 | 2026-11-19 | bar: 2026-11-08 to 2026-11-15
Conduct user feedback sessions for design validation | 2026-11-20 | 2026-11-26 | bar: 2026-11-15 to 2026-11-22
Review prototype with supervisor and gather feedback | 2026-11-22 | 2026-11-27 | bar: 2026-11-22
Refine UI and integrate UI snapshots into Chapter 4 ◆ | 2026-11-28 | 2026-12-03 | bar: 2026-11-22 to 2026-11-29
Phase 7: Final Report Compilation | 2026-11-15 | 2026-12-10
Draft abstract, acknowledgments, and conclusion sections | 2026-11-15 | 2026-11-22 | bar: 2026-11-15 to 2026-11-22
Compile chapters 1-4 into the SWE GP1 Template | 2026-11-23 | 2026-11-28 | bar: 2026-11-22
Format list of tables, figures, acronyms, and references | 2026-11-29 | 2026-12-02 | bar: 2026-11-29
Conduct final proofreading and formatting review | 2026-12-03 | 2026-12-07 | bar: 2026-11-29 to 2026-12-06
Submit Final Report to supervisor ◆ | 2026-12-08 | 2026-12-10 | bar: 2026-12-06
Phase 8: Project Presentation & Demo | 2026-12-01 | 2026-12-16
Outline presentation structure based on report chapters | 2026-12-01 | 2026-12-05 | bar: 2026-11-29
Create presentation poster focusing on design and results | 2026-12-06 | 2026-12-11 | bar: 2026-12-06
Prepare and test live demo/video of the clickable prototype | 2026-12-08 | 2026-12-13 | bar: 2026-12-06 to 2026-12-13
Conduct presentation rehearsal and timing checks | 2026-12-14 | 2026-12-16 | bar: 2026-12-13
Deliver Final Presentation ◆ | 2026-12-17 | 2026-12-17 | bar: 2026-12-13
Deadlines | Date
Project idea | 2026-10-01 | bar: 2026-09-27
Proposal | 2026-10-08 | bar: 2026-10-04
Final report | 2026-12-10 | bar: 2026-12-06
Presentation | 2026-12-17 | bar: 2026-12-13
Dark bars show each phase's span, lighter bars show its tasks, and ◆ marks the deadline week.